## Slide 1: IT4U - R0.9 High level project plan
6th December 2018

## Slide 2: HIGH LEVEL PLAN OF RELEASE 0.9
SEP
OCT
NOV
JAN
FEB
MAR
APR
2018
2019
DEC
W1
W2
W3
W4
W1
W2
W3
W4
W1
W2
W3
W4
W1
W2
W3
W4
W1
W2
W3
W4
W1
W2
W3
W4
W1
W2
W3
W4
W1
W2
W3
W4
Iteration 4
Iteration 2
Iteration 3
Development
Development
Fx
Development
Development
Fx
Development
Development
Fx
Fx
Fx
Fx
Set of features
Set of features
Set of features
Set of features
Set of features
Integration
Set of features
* Dates are subject to change depending on what happens with earlier releases
The development of release 0.9 will be broken into iterations with development phases (Sprints) within each iteration. There will then be a final iteration dedicated to integration with previous releases.

## Slide 3: Stakeholder engagement and involvement of release 0.9 development phase
There will be a continual involvement with the CTIS Governance using “0.9 Champions” to ensure agile engagement to support short development cycles. There will be Demos throughout development for visibility on features and progress to the entire CTIS Expert Group.
SEP
OCT
NOV
JAN
FEB
MAR
APR
2018
2019
DEC
W1
W2
W3
W4
W1
W2
W3
W4
W1
W2
W3
W4
W1
W2
W3
W4
W1
W2
W3
W4
W1
W2
W3
W4
W1
W2
W3
W4
W1
W2
W3
W4
Interactive sessions*
DEMO SESSIONS*
Iteration 4
Iteration 2
Development
Development
Fx
Development
Development
Fx
Development
Development
Fx
Fx
Fx
Fx
Iteration 3
Define demo paths
Approve demo paths
Define demo paths
Approve demo paths
Define demo paths
Define demo paths
Approve demo paths
Define demo paths
Approve demo paths
Define demo paths
Approve demo paths
Integration
Approve demo paths
Usability tests
0.9 Champions
CTIS Expert Group
The exact list of features that will be used in the demo are defined by the demo paths. They will be shared with the audience one week prior to the session.
* Dates are subject to change depending on what happens with earlier releases
0.9 Champions
IS1
IS2
IS3
IS4
IS5
IS6
Iteration 2
Iteration 3
Iteration 4

## Slide 4: HIGH LEVEL PLAN OF RELEASE 0.9
ITERATION 2 CONTENT
The functionalities that will be shown have been planned as follows:
Iteration 2
Sprint 1
Sprint 2
New Safety Reporting roles access.
Update personal information:
reset password, update employer, information
Assign or revoke role (Sponsor and Authority).
Approve or reject request (Sponsor and Authority).
Search for Users and user roles.
View new information of Safety reporting tasks, new UI.
Search for tasks, new UI.
Release, extend and assign tasks.
Create, validate and submit ASR.
Manage tasks related to ASR Submit.
Create the task Express Willingness/Unwillingness.
View alerts and notices related to ASR Submit.
View alerts and notices related to Safety reporting roles (Sponsor and Authority)
Search for notices and alerts.
Upload documents to ASR, new UI.
Remove documents.
Provide CT information to ADR.
Search and view ASR by Sponsor.

## Slide 5: HIGH LEVEL PLAN OF RELEASE 0.9
ITERATION 3: CONTENT
The functionalities that will be shown have been planned as follows:
Iteration 3
Sprint 3
Sprint 4
    Search and view ASR by MS.
    View task, alerts and notices related to Assessment (Initiate & Share)
    View task, alerts and notices related to Willingness or unwillingness
    Display and update new assessment form
    Verify new assessment functionalities
      NOTE*: Select saMS done by Data Base insert
    Manage considerations, all functionalities:
      Add considerations.
      Remove draft considerations.
      Display and list considerations.
    Select saMS for ASR Assessment.
    Express willingness or unwillingness.
    View task, alerts and notices related to Finalize assessment
    Consolidate considerations, all functionalities
    Request additional information (MS): all functionalities
    saMS finalizes assessment (without RFI)
    Display RFI List (Sponsor)
    View alerts and notices related to RFIs

## Slide 6: HIGH LEVEL PLAN OF RELEASE 0.9
ITERATION 4: CONTENT
The functionalities that will be shown have been planned as follows:
Iteration 4
Sprint 5
(*)The content of last Development Sprint is minor caused by the prioritization of new Use Cases implementation, and also considering it as an extra capacity to manage any previous deviation or remaining bug fixing.
    View ASR summary by MS.
    Assess additional information: all functionalities:
    Save, share, cancel
    Create, edit, submit an RFI
    Create a discussion on an RFI.
    View RFI and Respond to RFI: all functionalities
    Search for RFI.
    Download ASR details.
    Search & View ad-hoc assessment details:
    search and display information.
    Display ASR Assessment.
    Download ASR Assessment attached documents.
    Display ASR Submission with RFI information.
    Download ASR Submission attached documents.
    Search & View ad-hoc assessment details:
    download and clear search results